## Burndown Chart Example (hidden)
| Burn down chart | [6 empty] | Sprint 5 Burn Down Chart
|  | Burned down |  | Balance |  | Selesai Hari ini
| Hari | Rencana | Sebenarnya | Total | Aktual
2014-06-13 | 0 | 0 | 0 | 315 | 315 | 0
2014-12-01 | 1 | 13 | 8 | 302 | 307 | 8
2014-12-02 | 2 | 13 | 7 | 289 | 300 | 7 | Hours
2014-12-03 | 3 | 13 | 8 | 276 | 292 | 8
2014-12-04 | 4 | 13 | 8 | 263 | 284 | 8
2014-12-07 | 5 | 16.8 | 10.5 | 250 | 273.5 | 10.5
2014-12-08 | 6 | 16.8 | 12 | 233 | 261.5 | 12
2014-12-09 | 7 | 16.8 | 13 | 216 | 248.5 | 13 |  |  | Days
2014-12-10 | 8 | 16.8 | 18 | 199 | 230.5 | 18
2014-12-11 | 9 | 16.8 | 8.25 | 182 | 222.25 | 8.25
2014-12-14 | 10 | 17.2 | 7.5 | 166 | 214.75 | 7.5
2014-12-15 | 11 | 17.2 | 12 | 149 | 202.75 | 12
2014-12-16 | 12 | 17.2 | 8.25 | 132 | 194.5 | 8.25
2014-12-17 | 13 | 17.2 | 20 | 115 | 174.5 | 20
2014-12-18 | 14 | 17.2 | 20 | 98 | 154.5 | 20
2014-12-21 | 15 | 16 | 16.75 | 80 | 137.75 | 16.75
2014-12-22 | 16 | 16 | 0.75 | 64 | 137 | 0.75
2014-12-23 | 17 | 16 | 26.5 | 48 | 110.5 | 26.5
2014-12-24 | 18 | 8 | 8 | 40 | 102.5 | 8
2014-12-28 | 19 | 8 | 5.5 | 32 | 97 | 5.5
2014-12-29 | 20 | 8 | 2 | 24 | 95 | 2
2014-12-30 | 21 | 8 | 7 | 16 | 88 | 7
2014-12-31 | 22 | 8 | 8 | 8 | 80 | 8
2014-01-04 | x | 0 | 8 | 0 | 72 | 8
|  | 310 | 243
Signup for FREE E-mail Updates
Subscribe to PHD thru RSS
Follow PHD on Twitter
Visit Pointy Haired Dilbert Website and Learn More

## Burndown Chart Template
| Burn down chart | [6 empty] | Title
|  | Burned down |  | Balance |  | Daily Completed
| Day | Planned | Actual | Planned | Actual
2015-06-12 | 0 | 0 | 0 | 15 | 15 | 0
2015-06-13 | 1 | 5 | 6 | 10 | 9 | 6
2015-06-15 | 2 | 2 | 3 | 8 | 6 | 4 | Hours
2015-06-19 | 3 | 3 | 4 | 5 | 2 | 4
Days
Signup for FREE E-mail Updates
Subscribe to PHD thru RSS
Follow PHD on Twitter
Visit Pointy Haired Dilbert Website and Learn More